# Document 5 — Use of Funds Schedule

Use of Funds Schedule — USD 3.6M Expansion Capital

Internal working structure to be finalized through an approved ProjectCo budget before closing. All amounts ring-fenced for the current Isseksi expansion phase.

## Summary Allocation

| Category | Allocation | Amount (USD) |
| --- | --- | --- |
| Mobile processing station | 30% | 1,080,000 |
| Quarry preparation | 15% | 540,000 |
| Equipment and material handling | 15% | 540,000 |
| Working capital | 15% | 540,000 |
| Technical team and QA/QC | 8% | 288,000 |
| Water, ESG, and monitoring | 7% | 252,000 |
| Digital tracking and Data Room | 5% | 180,000 |
| Legal, governance, and transaction costs | 5% | 180,000 |
| Total | 100% | 3,600,000 |

### Mobile Processing Station — USD 1,080,000 (30%)

| Field | Detail |
| --- | --- |
| Purpose | Procurement, fabrication, delivery, and commissioning of the core mobile production unit: modular processing, leaching, cementation, and water recovery. |
| Timing | Initiated in Tranche 1 (planning, specification, procurement launch); main spend in Tranche 2; commissioning in Tranche 3. |
| Related tranche | Tranches 1–3 (core Tranche 2) |
| Expected output | Commissioned mobile green copper processing station ready for ramp-up. |
| Monitoring metric | Procurement milestones met; factory/site acceptance steps completed; commissioning report issued. |
| Risk if unfunded | No production capability — the expansion phase cannot generate output; all other spending is stranded. |

### Quarry Preparation — USD 540,000 (15%)

| Field | Detail |
| --- | --- |
| Purpose | Preparation of the four-quarry operating architecture: access, benches, sequencing, site readiness for staged feed to the mobile station. |
| Timing | Tranche 2, following the approved procurement and quarry plan. |
| Related tranche | Tranche 2 |
| Expected output | Four-quarry architecture prepared and sequenced for feed. |
| Monitoring metric | Quarry readiness checklist completed per plan; sequencing plan approved. |
| Risk if unfunded | Feed bottleneck — the mobile station is starved of material and ramp-up slips. |

### Equipment and Material Handling — USD 540,000 (15%)

| Field | Detail |
| --- | --- |
| Purpose | Loading, hauling, crushing support, and handling tools required to move material from quarry faces to the processing station. |
| Timing | Tranches 2–3, aligned to quarry readiness. |
| Related tranche | Tranches 2–3 |
| Expected output | Complete handling chain from quarry to station. |
| Monitoring metric | Equipment delivered, inspected, and operational; utilization tracked quarterly. |
| Risk if unfunded | Material movement gap — capacity mismatch between quarries and station. |

### Working Capital — USD 540,000 (15%)

| Field | Detail |
| --- | --- |
| Purpose | Labor, consumables, energy, logistics, and operating continuity through commissioning and ramp-up. |
| Timing | Drawn progressively across Tranches 1–3, weighted to Tranche 3. |
| Related tranche | Tranches 1–3 (core Tranche 3) |
| Expected output | Uninterrupted operations through ramp-up. |
| Monitoring metric | Cash runway and burn versus budget reported quarterly. |
| Risk if unfunded | Operational stoppage risk — execution interrupted by liquidity gaps. |

### Technical Team and QA/QC — USD 288,000 (8%)

| Field | Detail |
| --- | --- |
| Purpose | Sampling, assays, quality control, and production verification — the evidence discipline of the platform. |
| Timing | Tranches 1–3, continuous. |
| Related tranche | Tranches 1–3 |
| Expected output | Verified production quality and a defensible technical record. |
| Monitoring metric | QA/QC reports per protocol; assay program executed; nonconformities tracked. |
| Risk if unfunded | Loss of evidence discipline — output and claims cannot be verified; credibility for later rounds is damaged. |

### Water, ESG, and Monitoring — USD 252,000 (7%)

| Field | Detail |
| --- | --- |
| Purpose | Water discipline, environmental controls, and ESG monitoring around the processing and quarry operations. |
| Timing | Tranches 1–3, continuous from site activity start. |
| Related tranche | Tranches 1–3 |
| Expected output | Compliant water and environmental controls with monitored performance. |
| Monitoring metric | Water-use and monitoring indicators reported quarterly; corrective actions closed. |
| Risk if unfunded | Regulatory, environmental, and reputational exposure; ESG positioning undermined. |

### Digital Tracking and Data Room — USD 180,000 (5%)

| Field | Detail |
| --- | --- |
| Purpose | HYRION-supported reporting layer, production data capture, and the controlled investor Data Room with logged, permission-based access. |
| Timing | Tranche 1 setup; maintained through Tranches 2–3. |
| Related tranche | Tranche 1 (setup) |
| Expected output | Operational reporting and Data Room infrastructure supporting quarterly reviews. |
| Monitoring metric | Data Room current and logged; quarterly reports produced on time. |
| Risk if unfunded | Reporting discipline fails — investor confidence and governance quality degrade. |

### Legal, Governance, and Transaction Costs — USD 180,000 (5%)

| Field | Detail |
| --- | --- |
| Purpose | ProjectCo setup or designation, shareholders' agreement, subscription documents, protocols, and governance controls. |
| Timing | Tranche 1, at and around first closing. |
| Related tranche | Tranche 1 |
| Expected output | Complete, executed legal and governance framework. |
| Monitoring metric | Document checklist completed; governance protocol in force. |
| Risk if unfunded | Structural risk — the transaction lacks an enforceable, reviewable framework. |